THE MARKDOWN

Scrum Master

Backend Build | Sprint Plan | Task Tracker

Justin "Yeti" Kuiper | Updated March 7, 2026

# Project Overview

The Markdown is the production front-end for the Non Sequitur news aggregator ecosystem. It ingests RSS feeds into WordPress, curates content into seven daily blocks (00-06), and enables a quick-publish pipeline to push commentary across five social platforms (X, LinkedIn, Instagram, YouTube, Medium). Every piece of content links back to owned property at justin-kuiper.com.

## Block Architecture

| Block | Domain | Position | Content Types | Push Platforms |
| --- | --- | --- | --- | --- |
| 00 | HERO | Full-Width | Breaking news, flagship features, major announcements | X, LinkedIn, Medium |
| 01 | AI / GEN AI | Left Top | Model releases, AI policy, enterprise AI, tools, research | X, LinkedIn, Medium, YouTube |
| 02 | CYBER | Left Bottom | Threat intel, breaches, vulns, policy, CISO perspectives | X, LinkedIn, Medium |
| 03 | INNOVATION | Center Top | Emerging tech, startups, R&D, cross-domain convergence | X, LinkedIn, Instagram, Medium |
| 04 | FNW | Center Bottom | Reflections, devotionals, stoic philosophy, personal growth | Instagram, X, Medium, YouTube |
| 05 | SPACE / AERO | Right Top | Launches, missions, defense/aero, satellite, space policy | X, LinkedIn, YouTube, Medium |
| 06 | DIGITAL LIFE | Right Bottom | Personal tech, gadgets, gaming, culture, creator economy | X, Instagram, YouTube |

# Completed Deliverables

| Deliverable | Notes | Owner | Status |
| --- | --- | --- | --- |
| Project Handover Doc | Original Non Sequitur concept: 2-lane pipeline, 7-slot framework, platform routing, thematic arc | Yeti | DONE |
| Production Requirements | 50+ line items: WordPress config, RSS pipeline (40 feeds), editorial layer, platform publishing, AI/Claude, DevOps, cost estimate | Yeti / AI | DONE |
| Backend Requirements | 9-section architecture: 4-layer system, WP data model (ns_feed_item CPT, 15 fields), 8-step quick-publish, 5 platform APIs, AI engine, 3-phase plan | Yeti / AI | DONE |
| The Markdown Prototype (HTML) | Live dark-mode Drudge-style layout. 7 blocks, 3 commentary styles, platform push tags, military time, domain color coding. Deployed to GitLab Pages. | Yeti / AI | DONE |
| GitLab Repo (JK.com-ver02) | All deliverables pushed. GitLab Pages live at jk-com-ver02-5480e0.gitlab.io | AI | DONE |

# Backend Build — Sprint Plan

## Sprint 1: Foundation (Weeks 1-2)

Goal: WordPress data model live, RSS feeds ingesting, basic editorial dashboard functional, Claude scoring items.

| # | Task | Acceptance Criteria | Owner | Est. | Status |
| --- | --- | --- | --- | --- | --- |
| 1A — WordPress Data Model |  |  |  |  |  |
| 1.1 | Register ns_feed_item CPT | CPT visible in admin, supports title/content/thumbnail | AI | 2h | PENDING |
| 1.2 | Register custom taxonomies (content_domain, thematic_arc, item_status, platform_published) | 4 taxonomies with correct terms, assignable to ns_feed_item | AI | 2h | PENDING |
| 1.3 | Register all 15 custom meta fields | All meta fields registered, visible in REST API, editable in admin | AI | 3h | PENDING |
| 1.4 | Build admin columns (domain color, score, status, block) | ns_feed_item list view shows colored domain tags, score badges, status, block # | AI | 3h | PENDING |
| 1B — RSS Ingest Pipeline |  |  |  |  |  |
| 1.5 | Install & configure WP RSS Aggregator Pro | Plugin active, license valid, import template mapped to ns_feed_item | Yeti | 2h | PENDING |
| 1.6 | Configure 40 starter RSS feeds across 6 domains | 40 feeds active, importing on schedule, auto-tagged by domain | Yeti / AI | 4h | PENDING |
| 1.7 | Build keyword-based auto-domain tagging rules | New items auto-classified into correct domain taxonomy based on source + keywords | AI | 3h | PENDING |
| 1.8 | Dedup logic (URL + title similarity) | No duplicate items in feed. Items within 90% title similarity flagged. | AI | 2h | PENDING |
| 1C — Claude / Gunther Integration |  |  |  |  |  |
| 1.9 | Build Claude feed scoring task (every 4h) | New items scored 1-10 on relevance. Score written to meta. Runs on cron. | AI | 4h | PENDING |
| 1.10 | Build Claude morning digest (daily 0600 CST) | Email sent with top 20 items grouped by domain, scores, arc alignment | AI | 3h | PENDING |
| 1D — Editorial Dashboard |  |  |  |  |  |
| 1.11 | Build DEV feed admin dashboard | Filterable list of all items by domain, score, status. Sort by score/date. | AI | 4h | PENDING |
| 1.12 | Build promote-to-PROD + block assignment UI | One-click promote with dropdown for block 00-06. Status updates to PROMOTED. | AI | 4h | PENDING |
| 1E — Front-End Template |  |  |  |  |  |
| 1.13 | Build WordPress page template for The Markdown | 7-block layout renders from promoted ns_feed_items. Matches prototype design. | AI | 6h | PENDING |
| 1.14 | Deploy page as tab on justin-kuiper.com | The Markdown accessible via nav tab. Responsive. Dark mode. | Yeti / AI | 2h | PENDING |

Sprint 1 Total Estimate: ~44 hours

## Sprint 2: Quick-Publish Pipeline (Weeks 3-5)

Goal: All 5 social platform APIs connected, AI reformatting engine live, quick-publish admin panel functional, commentary cards rendering on front-end.

| # | Task | Acceptance Criteria | Owner | Est. | Status |
| --- | --- | --- | --- | --- | --- |
| 2A — Social Platform API Integrations |  |  |  |  |  |
| 2.1 | X (Twitter) API v2 integration | OAuth 2.0 PKCE auth, tweet/thread creation, URL callback stored | AI | 6h | PENDING |
| 2.2 | LinkedIn Community Management API | OAuth 2.0, personal profile posting, URL callback stored | AI | 6h | PENDING |
| 2.3 | Instagram Graph API integration | Facebook App approved, container-based publish, image upload, permalink stored | Yeti / AI | 8h | BLOCKED |
|  | ⚠ BLOCKER: Facebook App Review (2-4 weeks). Submit ASAP. | App submitted for instagram_content_publish permission | Yeti | 1h | NEXT |
| 2.4 | YouTube Data API v3 (community posts) | OAuth 2.0, community post creation, URL callback stored | AI | 4h | PENDING |
| 2.5 | Medium API integration | Integration token auth, draft creation with canonical URL, tags | AI | 3h | PENDING |
| 2B — AI Content Engine |  |  |  |  |  |
| 2.6 | Build AI reformatting engine (5 platform versions from 1 input) | Single editorial note → X thread + LinkedIn post + IG caption + YT community + Medium draft | AI | 6h | PENDING |
| 2.7 | Build platform-specific prompt templates | Tone, length, format rules per platform. Link-back included. Hashtag strategies. | AI | 4h | PENDING |
| 2C — Quick-Publish Admin Panel |  |  |  |  |  |
| 2.8 | Build inline commentary editor (quick-edit panel) | Click item → write commentary in-panel (no page reload). Free-text + rich editor. | AI | 5h | PENDING |
| 2.9 | Build platform toggle checkboxes + blog draft toggle | 5 platform toggles + blog toggle. Block-specific defaults pre-checked. | AI | 3h | PENDING |
| 2.10 | Build side-by-side platform preview | All 5 versions rendered side-by-side. Each editable before publish. | AI | 5h | PENDING |
| 2.11 | Build publish button + API dispatch | Single click sends to all toggled platforms. URLs captured. Status → PUBLISHED. | AI | 5h | PENDING |
| 2D — Front-End Commentary Cards |  |  |  |  |  |
| 2.12 | Build commentary card components (tweet/pullquote/inline) | 3 card styles render in blocks. Click opens live social post. Configurable per block. | AI | 4h | PENDING |
| 2.13 | Build blog draft auto-creation with SEO fields | Toggle creates WP draft with template, SEO meta, canonical URL, social cross-links | AI | 4h | PENDING |
| 2.14 | Gunther seven-block summary for standup | Daily 0800 CST: one-line per block in morning briefing | AI | 2h | PENDING |

Sprint 2 Total Estimate: ~66 hours

## Sprint 3: Polish & Scale (Weeks 6-10)

Goal: Canva visual cards, auto-refresh, token management, archive, analytics, Instagram Stories, YouTube video pipeline.

| # | Task | Acceptance Criteria | Owner | Est. | Status |
| --- | --- | --- | --- | --- | --- |
| 3A — Visual & Branding |  |  |  |  |  |
| 3.1 | Canva MCP visual card generation | Branded cards auto-generated per domain. Used for IG + X + blog featured images. | AI | 6h | PENDING |
| 3.2 | Canva template design (6 domain templates) | One branded card template per domain with color coding + Non Sequitur branding | Yeti / AI | 4h | PENDING |
| 3B — Infrastructure |  |  |  |  |  |
| 3.3 | Token refresh automation (daily cron) | All 5 platform tokens checked daily. Auto-refresh if expiring within 7 days. Email alert if manual re-auth needed. | AI | 4h | PENDING |
| 3.4 | Rate limit handler + queue system | Retry with exponential backoff. Rate headers monitored. Queue prevents burst. | AI | 4h | PENDING |
| 3.5 | Audit logging for all publish actions | Custom log table: timestamp, platform, post URL, item ID, user | AI | 3h | PENDING |
| 3.6 | Front-end auto-refresh (AJAX polling every 15min) | Blocks update without full page reload. REST API endpoint returns block data. | AI | 3h | PENDING |
| 3C — Scale Features |  |  |  |  |  |
| 3.7 | Archive page (historical daily editions) | Filterable by date, domain, thematic arc. Accessible from footer. | AI | 4h | PENDING |
| 3.8 | Instagram Stories support | Ephemeral content for breaking news. Image-only in MVP. | AI | 4h | PENDING |
| 3.9 | YouTube video pipeline (weekly roundup) | AI-scripted roundup + Canva thumbnail + upload. 1,600 quota units. | Yeti / AI | 8h | PENDING |
| 3.10 | Analytics dashboard (cross-platform) | Engagement metrics aggregated across all platforms. Content performance tracking. | Yeti / AI | 8h | PENDING |
| 3.11 | Subdomain: markdown.justin-kuiper.com | DNS configured. WordPress routing. SSL cert. | Yeti | 1h | PENDING |
| 3.12 | Feed health monitoring + alerts | Broken feeds detected. Dashboard widget. Email alert to Yeti. | AI | 3h | PENDING |

Sprint 3 Total Estimate: ~52 hours

# Blockers & Risks

| Blocker | Impact | Mitigation | Status |
| --- | --- | --- | --- |
| Facebook App Review for Instagram | Cannot automate Instagram posting until approved. 2-4 week timeline. Submit immediately. | Submit Week 1 | BLOCKED |
| X API Free Tier Limits | 1,500 tweets/month on free. May need Basic ($100/mo) for volume. | Monitor usage | PENDING |
| YouTube Quota (10K/day) | Community posts ~50 units each. Video upload 1,600. Manageable but must track. | Batch wisely | PENDING |
| Medium API (Drafts Only) | Medium API creates drafts, not live posts. Manual publish step required in Medium UI. | Acceptable | ACCEPTED |

# Operating Principles

The mission defines the architecture. The architecture secures the mission.

- Operational Triad: ARCHITECT (mission → design) → HARDEN (security from concept) → SCALE (fungible packaging)

- Process: IDENTIFY → CODIFY → PACKAGE → DEPLOY

- Every social post links back to owned property. The Markdown is the gravity well.

- Yeti is stakeholder & primary SME. AI is product owner & execution engine.

- GitLab is source of truth. All config versioned. Short-lived PATs only.

## Quality Gates

- Gate 1: Architectural Polish — Production ready. No rough edges. Responsive.

- Gate 2: Threat Modeled & Secure — All tokens encrypted. No credentials in repos. Rate limits handled.

- Gate 3: Social Pipeline Verified — All 5 platforms tested end-to-end. Link-back confirmed. Commentary cards live.