## Evaluation Scorecard
Project Evaluation Scorecard — Yeti Knowledge Systems
Robo Stack vs Content Ops ¦ Scale: 1 (Low) – 5 (High)
Criterion | Robo | Content | Robo Stack Rationale | Content Ops Rationale
FEASIBILITY & EFFORT
Technical complexity | 4 | 3 | Multi-tool K8s + cloud infra; many moving parts | Workflow tooling on existing platforms; simpler stack
Time to MVP | 2 | 4 | Needs K8s setup, CI/CD, multi-agent orchestration | Blog pipeline POC achievable in weeks
Resource requirements | 3 | 4 | Cloud costs, multiple AI tool licenses | Mostly existing tools; Notion/Obsidian + AI prompts
Dependency risk | 2 | 3 | Heavy reliance on 3rd-party AI tool licensing | Lighter dependencies; prompt-based approach
Operational overhead | 2 | 4 | Ongoing infra maintenance & security patching | Mostly content ops; low infra burden
REVENUE POTENTIAL
Time to first dollar | 2 | 4 | Needs demo-ready stack before selling consulting | Content outputs can start generating audience quickly
Recurring revenue potential | 4 | 3 | Enterprise stack setup + ongoing support contracts | Indirect via audience; sponsorship/subscription later
Market demand clarity | 3 | 3 | AI dev tooling is hot but crowded | Content ops is niche but personally aligned
Price point strength | 4 | 2 | Enterprise rates $125-200/hr; $10-30K engagements | Monetization path less defined at this stage
Scalability | 3 | 3 | Consulting scales with headcount, not infinitely | Content compounds but requires creator involvement
STRATEGIC VALUE
Brand positioning | 4 | 4 | Positions YKS as AI-forward technical consultancy | Positions Non Sequitur as thought leadership platform
Portfolio/IP value | 4 | 3 | GitHub demos, architecture artifacts, reusable IaC | Content library, editorial system IP
Synergy between projects | 4 | 4 | Stack can power Content Ops infrastructure | Content Ops can showcase & market Robo Stack
Long-term moat | 3 | 3 | Architecture expertise; security hardening niche | Unique voice + systematized content engine
Personal alignment | 3 | 5 | Strong technical fit; less creative expression | Deeply aligned with creator identity & mission
CATEGORY AVERAGES
Feasibility & Effort
Revenue Potential
Strategic Value
OVERALL SCORE

## Robo Stack Backlog
ID | Epic / Story | Acceptance Criteria | Points | Priority | Sprint | Dependencies | Type
LEGEND: Yellow = Evaluation Gate ¦ Green = Stakeholder Touchpoint
E1 | EPIC: Local Dev Environment Setup |  |  | P0
S1.1 | Set up Ubuntu workstation with K3s | K3s cluster running; kubectl verified | 5 | P0 | S1 |  | Build
S1.2 | Configure local Docker registry | Images push/pull locally | 3 | P0 | S1 | S1.1 | Build
S1.3 | Install and configure IDE tooling | VS Code + extensions operational | 2 | P1 | S1 |  | Build
EV1.1 | EVAL: K3s vs MicroK8s vs Docker Desktop | Decision doc with perf benchmarks, resource usage, and ease of client replication. Recommendation selected. | 3 | P0 | S1 | S1.1 | Eval Gate
TP1 | TOUCHPOINT: Sprint 1 Review with Yeti | Demo local dev env running. Review K8s choice rationale. Confirm direction for AI agent layer. Go/no-go for Sprint 2. | 1 | P0 | S1 | EV1.1 | Touchpoint
E2 | EPIC: AI Agent Integration Layer |  |  | P0
S2.1 | Integrate GitHub Copilot into workflow | Copilot suggestions active in IDE | 3 | P0 | S2 | S1.3 | Build
S2.2 | Set up TabbyML as local fallback | TabbyML running on local GPU/CPU | 5 | P1 | S2 | S1.1 | Build
S2.3 | Evaluate CodeWhisperer + JetBrains AI | Comparison doc with pros/cons/cost | 3 | P1 | S2 |  | Build
EV2.1 | EVAL: AI Agent Best-of-Breed Selection | Head-to-head comparison: code quality, latency, cost, licensing terms for consulting resale. Final agent stack selected. | 5 | P0 | S2 | S2.1-S2.3 | Eval Gate
TP2 | TOUCHPOINT: Sprint 2 Review with Yeti | Demo AI agents in action. Present eval results. Confirm agent stack selection. Review licensing for commercial use. | 1 | P0 | S2 | EV2.1 | Touchpoint
S2.4 | Build agent orchestration layer | Multi-agent routing functional per selected stack | 8 | P0 | S3 | TP2 | Build
E3 | EPIC: CI/CD Pipeline |  |  | P0
S3.1 | Configure Git repo with branch strategy | Main/dev/feature branches; protection rules | 3 | P0 | S2 |  | Build
EV3.1 | EVAL: CI/CD Platform — GitHub Actions vs GitLab CI vs Jenkins | Cost, complexity, portability for client engagements. Decision doc. | 3 | P0 | S3 | S3.1 | Eval Gate
S3.2 | Build CI pipeline (lint, test, build) | Automated pipeline on push using selected platform | 5 | P0 | S3 | EV3.1 | Build
S3.3 | Add security scanning to pipeline | Dependency + SAST scans on every PR | 5 | P1 | S3 | S3.2 | Build
TP3 | TOUCHPOINT: Sprint 3 Review with Yeti | Demo full CI/CD pipeline. Show orchestration layer. Review security scan approach. Go/no-go for cloud infra phase. | 1 | P0 | S3 | S3.3 | Touchpoint
E4 | EPIC: Cloud Infrastructure (AWS) |  |  | P1
EV4.1 | EVAL: AWS vs Azure vs GCP for target client base | Cost comparison, service parity, client preference data. Validated against consulting market. | 3 | P0 | S4 |  | Eval Gate
S4.1 | Terraform VPC + networking module | VPC with public/private subnets deployed | 5 | P1 | S4 | EV4.1 | Build
S4.2 | EC2 compute provisioning module | Dev instances launchable via Terraform | 5 | P1 | S4 | S4.1 | Build
S4.3 | IAM least-privilege policy setup | Role-based access; no root usage | 3 | P0 | S4 | S4.1 | Build
TP4 | TOUCHPOINT: Sprint 4 Review with Yeti | Demo cloud infra provisioning. Review actual AWS costs vs estimates. Validate cloud choice. Go/no-go for EKS. | 1 | P0 | S4 | S4.3 | Touchpoint
S4.4 | Optional EKS cluster module | EKS deployable for client demos | 8 | P2 | S5 | TP4 | Build
E5 | EPIC: Security Hardening |  |  | P0
S5.1 | Implement encrypted API comms | TLS everywhere; no plaintext API calls | 3 | P0 | S4 |  | Build
EV5.1 | EVAL: Logging Stack — CloudWatch vs ELK vs Datadog | Cost at scale, query capability, client portability. Decision doc. | 3 | P1 | S5 |  | Eval Gate
S5.2 | Centralized logging (selected platform) | Logs aggregated; alerting configured | 5 | P1 | S5 | EV5.1 | Build
S5.3 | Supply-chain scanning integration | Automated dependency audit on build | 3 | P1 | S5 | S3.2 | Build
TP5 | TOUCHPOINT: Sprint 5 Review with Yeti | Full security posture review. Demo logging + alerting. Confirm stack is demo-ready. Define reference app scope. | 1 | P0 | S5 | S5.3 | Touchpoint
E6 | EPIC: Demo & Commercialization |  |  | P1
S6.1 | Build reference application demo | End-to-end app deployed via stack | 8 | P1 | S6 | TP5 | Build
S6.2 | Publish GitHub portfolio artifacts | Public repo with docs + IaC modules | 5 | P1 | S6 | S6.1 | Build
EV6.1 | EVAL: Consulting Package Pricing vs Market | Competitive analysis of AI consulting rates. Validate $125-200/hr against market. Package tier validation. | 3 | P1 | S7 |  | Eval Gate
S6.3 | Create consulting service packages | 3-tier pricing doc ready | 3 | P1 | S7 | EV6.1 | Build
TP6 | TOUCHPOINT: Final Review with Yeti | Full stack demo. Walk through portfolio. Review pricing packages. Final go/no-go for commercial launch. | 1 | P0 | S7 | S6.3 | Touchpoint

## Content Ops Backlog
ID | Epic / Story | Acceptance Criteria | Points | Priority | Sprint | Dependencies | Type
LEGEND: Yellow = Evaluation Gate ¦ Green = Stakeholder Touchpoint
E1 | EPIC: Capture & Clarify System |  |  | P0
EV1.1 | EVAL: Notion vs Obsidian vs Hybrid for Content OS | Feature comparison: capture speed, mobile access, API/automation, export, cost. Decision doc with recommendation. | 5 | P0 | S1 |  | Eval Gate
S1.1 | Design idea capture schema | Template with fields: signal, source, tags, status — on selected platform | 3 | P0 | S1 | EV1.1 | Build
S1.2 | Build quick-capture workflow | Ideas capturable in < 30 seconds from mobile + desktop | 3 | P0 | S1 | S1.1 | Build
S1.3 | Create clarification prompt library | 10+ prompts for idea refinement, tested against real ideas | 5 | P0 | S1 |  | Build
EV1.2 | EVAL: AI Prompt Engine — ChatGPT vs Claude vs Custom | Evaluate prompt quality, API cost, workflow integration for editorial prompts. Decision doc. | 3 | P0 | S1 | S1.3 | Eval Gate
TP1 | TOUCHPOINT: Sprint 1 Review with Yeti | Demo capture workflow. Review platform selection. Test quick-capture UX live. Confirm prompt engine choice. Go/no-go for pipeline build. | 1 | P0 | S1 | EV1.2 | Touchpoint
E2 | EPIC: Editorial Pipeline (Blog) |  |  | P0
S2.1 | Define stage gates: Shape → Develop → Refine | Clear criteria for each transition, documented in Markdown | 3 | P0 | S2 | TP1 | Build
S2.2 | Build Kanban board for content lifecycle | Board with columns matching workflow stages | 2 | P0 | S2 | S2.1 | Build
S2.3 | Create stage-specific AI prompt sets | Prompts for each stage (expand, critique, polish) — tested on 3+ real pieces | 5 | P0 | S2 | S2.1 | Build
EV2.1 | EVAL: Blog Platform — Ghost vs WordPress vs Substack vs Custom | Evaluate: ownership, SEO, design control, newsletter integration, cost. Decision doc. | 3 | P0 | S2 |  | Eval Gate
S2.4 | Implement Package → Queue → Publish flow | Content queued with metadata; publish schedule; connected to selected blog platform | 5 | P1 | S3 | EV2.1 | Build
TP2 | TOUCHPOINT: Sprint 2 Review with Yeti | Demo full editorial pipeline. Walk through a real idea from capture to publish-ready. Review blog platform choice. Go/no-go for cadence system. | 1 | P0 | S2/S3 | S2.3 | Touchpoint
E3 | EPIC: Thematic Arc & Cadence System |  |  | P1
S3.1 | Design thematic arc planning template | Monthly arc with weekly topic slots | 3 | P1 | S3 | TP2 | Build
S3.2 | Build weekly production cycle checklist | Repeatable weekly cadence with task list | 3 | P1 | S3 | S3.1 | Build
S3.3 | Create derivative content generation rules | Rules for blog → social, blog → newsletter — documented and tested | 5 | P1 | S4 | S2.4 | Build
TP3 | TOUCHPOINT: Sprint 3/4 Review with Yeti | Review first month of cadence. Assess content quality and volume. Review derivative rules. Go/no-go for social expansion. | 1 | P1 | S4 | S3.3 | Touchpoint
E4 | EPIC: Social Media Integration |  |  | P2
S4.1 | Define short-form output templates | Templates for Twitter/X, LinkedIn, Instagram — brand-consistent | 3 | P2 | S4 | TP3 | Build
S4.2 | Build blog-to-social transformation prompts | AI prompts that extract social posts from blog content | 5 | P2 | S5 | S4.1 | Build
EV4.1 | EVAL: Scheduling Tools — Buffer vs Hootsuite vs Typefully vs Native | Evaluate: multi-platform support, analytics, cost, automation capability. Decision doc. | 3 | P2 | S5 |  | Eval Gate
S4.3 | Set up scheduling/distribution tooling | Selected tool configured and tested | 3 | P2 | S5 | EV4.1 | Build
TP4 | TOUCHPOINT: Sprint 5 Review with Yeti | Demo social integration end-to-end. Review engagement analytics approach. Confirm readiness for multimedia phase. | 1 | P2 | S5 | S4.3 | Touchpoint
E5 | EPIC: Multimedia Expansion |  |  | P3
EV5.1 | EVAL: Podcast Hosting — Anchor vs Buzzsprout vs Transistor vs Riverside | Evaluate: recording quality, distribution, analytics, monetization options. Decision doc. | 3 | P3 | S6 |  | Eval Gate
S5.1 | Design podcast episode pipeline | Workflow from topic → script → record → edit → publish on selected host | 5 | P3 | S6 | EV5.1 | Build
EV5.2 | EVAL: Video Pipeline — YouTube Studio vs custom editing workflow | Evaluate: editing tools, thumbnail generation, SEO tooling, workflow integration. Decision doc. | 3 | P3 | S6 |  | Eval Gate
S5.2 | Design YouTube vlog pipeline | Workflow from concept → script → shoot → edit → publish | 8 | P3 | S7 | EV5.2 | Build
S5.3 | Integrate multimedia into content calendar | Unified calendar across all channels | 5 | P3 | S7 | S5.1, S5.2 | Build
TP5 | TOUCHPOINT: Final Review with Yeti | Full ecosystem demo: capture → blog → social → podcast → video. Review operational cadence sustainability. Final go/no-go for full production mode. | 1 | P0 | S7 | S5.3 | Touchpoint